## Rescope
Worm VIP Fall 2023
Nathaly Jose-Maria
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |  |  | 10 | 11 | 12 | 13 | 14 | Week #
[5 empty] | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 |  |  | 12 | 13 | 14 | 15 | 16 | Semester Week #
Task |  | Progress | Start | End | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-24 | 2023-05-01 | 2023-06-12 | 2023-06-26 | 2023-07-03 | 2023-07-10 | 2023-07-17 | 2023-07-24 | 2023-07-31 | 2023-08-07 | 2023-08-14 | 2023-08-21 | 2023-08-28 | Monday
Deliverables
Midterm Notebook Check |  | DONE | 2023-06-12 | 2023-06-21 | bar: 6 8
Final Notebook Check |  |  | 2023-07-31 | 2023-08-07
Final Report |  |  | 2023-07-31 | 2023-08-07
Preparations
Create Project Plan |  | DONE | 2023-03-13 | 2023-03-14 | bar: 1 3
Review Previous Work |  | DONE | 2023-03-13 | 2023-03-14 | bar: 1 3
Ensure PACE Functionality |  | DONE | 2023-03-14 | 2023-03-26 | bar: 1 3 to 2 4
Succesfully Run Kaggle Code (Small Sample Size)
Import Code into PACE |  | DONE | 2023-03-27 | 2023-04-18 | bar: 3 5 to 4 6
Attempt 1 on Remote Desktop |  | DONE | 2023-04-24 | 2023-05-03 | bar: 4 6
Attempt on Local Desktop - Recreate Code Locally | bar: 5 7 to 9 11
1. TensorFlow Object Detection API Setup |  | DONE | 2023-05-03 | 2023-06-15 | bar: 5 7 to 6 8
2. Import Dependencies |  | DONE | 2023-06-15 | 2023-06-21 | bar: 6 8
3. Explore the data sets |  |  | 2023-06-28 | bar: 7 9
4. Train an object detection model |  |  | 2023-06-28 | bar: 7 9
5. Setup Tensorboard to monitor training progress |  |  | 2023-07-03 | bar: 7 9 to 8 10
6. Export a model for inference |  |  | 2023-07-03 | bar: 8 10
7. Model Evaluation |  |  | 2023-07-10 | bar: 8 10 to 9 11
Tweak for Guaranteed Recreation |  |  | 2023-07-10 | [12 empty] | ~ | bar: 8 10 to 9 11
Sucessfully Run Kaggle Code (Expected Sample Size)
Code Blocks 1-3 |  |  | 2023-07-31
Code Blocks 4-6 |  |  | 2023-07-31
Tweak for Guaranteed Recreation |  |  | 2023-08-07
Manipulations (Stretch Goals - Ordered by Priority DESC)
Base Pre-Trained Model |  |  | 2023-08-14
Batch Size |  |  | 2023-08-21 | [14 empty] | ~
Training Steps |  |  | 2023-08-21
False Glitter Set |  |  | 2023-08-28 | [15 empty] | ~
Note on E36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: had to change; running into difficulties with VPN on current WiFi so may delay work. will update as things change.
Note on A49: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I like how you have specifically identified this as a stretch goal Reply: as a heads up, I should have a dataset of worms images for you to work with sometime in April. Please check back

## Fall 2023
Worm VIP Fall 2023
Nathaly Jose-Maria
|  |  |  | 1 | 2 | 3 | X | X | X | 4 | 5 | X | X | X | X | X | 6 | 7 |  | 8 | 9 | 10 | 11 | 12 | 13 | 14 | Week #
|  |  |  | 3 | 4 | 5 | X | X | X | 6 | 7 | X | X | X | X | X | 8 | 9 |  | 10 | 11 | 12 | 13 | 14 | 15 | 16 | Semester Week #
Task | Progress | Start | End | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 2023-06-12 | 2023-06-19 | 2023-06-26 | 2023-07-03 | 2023-07-10 | 2023-07-17 | 2023-07-24 | 2023-07-31 | 2023-08-07 | 2023-08-14 | Monday
Deliverables
Midterm Notebook Check |  | 2023-06-19
Final Notebook Check |  | 2023-07-31 | 2023-08-07
Final Report |  | 2023-07-31 | 2023-08-07
Preparations
Create Project Plan | DONE | 2023-03-13 | 2023-03-14
Review Previous Work | DONE | 2023-03-13 | 2023-03-14
Ensure PACE Functionality | DONE | 2023-03-14 | 2023-03-26
Recreate Kaggle Code
Import Code into PACE | DONE | 2023-03-27 | 2023-04-18
Run Small Sample Size | WIP | 2023-04-24
Run Expected Sample Size | WIP | 2023-04-24
Experiment with Kaggle Code (Priority/Difficulty)
(!/!) Class Label Mapping |  | 2023-06-26
(!!/!!) Batch Size |  | 2023-06-26
(!!/!!) Model Pipeling Configuration |  | 2023-07-03 | [20 empty] | ~
(!!/!!) Training Steps |  | 2023-07-03
(!!!/!!!) Base Pre-Trained Model |  | 2023-07-03 | [20 empty] | ~
Summary of Findings |  | 2023-07-17
Implementation of Alternate Algorithms
Beaudelaire Diagnosis Paper |  | 2023-07-24 | [20 empty] | ~ |  |  | ~
Circular Object Detection |  | 2023-07-24 | [20 empty] | ~ |  |  | ~
Akintayo Nematode Paper |  | 2023-07-24 | [20 empty] | ~ |  |  | ~
Experiment with Various Data Sets (Stretch Goal)
False Glitter Set |  | 2023-07-31 | [22 empty] | ~ | ~
Portions of Actual Data |  | 2023-07-31 | [22 empty] | ~ | ~
~ indicates room for error; shaded means the task will likely take the majority of the week, unshaded means will likely not
Note on J3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Took a necessary two week break following return to the states to resolve personal issues prior to continuing
Note on E16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: had to change; running into difficulties with VPN on current WiFi so may delay work. will update as things change.
Note on A29: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I like how you have specifically identified this as a stretch goal Reply: as a heads up, I should have a dataset of worms images for you to work with sometime in April. Please check back
Note on B33: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I think your timeline looks good. A couple points: 1) I like how you have specifically identified experimenting with data sets as a stretch goal. As a heads up, I should have a dataset of worms images for you to work with sometime in April. Please check back. 2) Be sure to allot time to figure out how to utilize pace. I think that's what you mean by "Ensure Pace functionality". There are a number of resources available online through CoC to learn, fyi Reply: 2) Yup, I've started delving into the PACE documentation, and I agree I might need more time. As such, I might shift everything by a week, but I already anticipated the potential for an additional week thankfully, I'll be sure to update this plan as I move forward.